## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TEAM MEMBER(s) | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | S1 | [11 empty] | S2 |  |  |  |  | M1 |  | S3 | [6 empty] | S4 |  |  |  |  | M2 |  | S5 | [6 empty] | S6 | [6 empty] | S7 | [9 empty] | M3
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Everyone | Play the game | 1 | 10 | 4 | 10 | 100%
Everyone | Make 3 user stories | 12 | 4 | 14 | 4 | 100%
Everyone | Find Code Smells | 21 | 4 | 22 | 5 | 100%
Everyone | Review Code Smells | 22 | 3 | 23 | 4 | 100%
Everyone | Code metrics reports | 26 | 2 | 27 | 3 | 100%
Everyone | Design patterns | 26 | 4 | 27 | 4 | 100%
Everyone | Use case diagrams | 26 | 3 | 28 | 4 | 100%
Everyone | Update all User Stories | 36 | 1 | 38 | 1 | 100%
Everyone | Create Use Cases | 37 | 3 | 38 | 2 | 100%
Everyone | Use Case text description | 37 | 3 | 38 | 2 | 100%
Everyone | Implement 1st version User Story | 41 | 5 | 42 | 5 | 100%